## dev-sprint-planning
Dev Sprint Planning
Module 4
Name | Assignee | Status | Epic | Priority | Estimation | Confidence
Data analyser meet up | Team | On hold | GUI | Medium | 2 | 4
Intregation of formula | Demba, Oumou | Waiting for deployment | GUI | Best effort | 22 | 3
Graphs generation | Demba, Oumou, Amine | Waiting for review | GUI | Best effort | 4 | 3
[5 empty] | 28 | 3.3/5
Module 3
Name | Assignee | Status | Epic | Priority | Estimation | Confidence
Data explorer meet up | Team | Done | GUI | Medium | 2 | 3
Map integration in GUI | Demba, Ousmane E | Waiting for review | GUI | Best effort | 18 | 2
Connecting DB to map | Demba, Oumou | Done | GUI | Best effort | 12 | 5
Fixing bugs | Demba, Ousmane E | Stuck | GUI | Best effort | 10 | 2
Module review | Team | Ongoing |  | Medium | 1 | 5
[5 empty] | 43 | 3.4/5
Module 1
Name | Assignee | Status | Epic | Priority | Estimation | Confidence
Data acquisition meet up | Team | Done |  | Best effort | 4 | 5
Downloading all pdfs in one script | Amidou, Amine | Done | Download | High | 72 | 4
Pdf review | Amidou, Demba | Done | Security | Medium | 5 | 3
Parse data in a json file | Amidou, Amine | Done | Parsing | High | 90 | 4
GUI integration | Ousmane E, Ousmane Sow | Done |  | High | 8 | 3
Sprint review | Team | Done |  | Medium | 1 | 5
[5 empty] | 180 | 3.8/5
Module 2
Name | Assignee | Status | Epic | Priority | Estimation | Confidence
Data loader meet up | Team | Done | GUI | Best effort | 3 | 5
GUI first sample design | Ousmane S, Ousmane E | Done | GUI | Best effort | 16 | 4
Database Creation and design | Team | Done | DB | Best effort | 4 | 3
GUI design validated | Team | Done | GUI | Medium | 1 | 4
Implementation of different features | Ousmane S, Ousmane E | Done | GUI | High | 13 | 3
Selection of JSON files feature | Ousmane S, Ousmane E | Done | GUI | Medium | 11 | 3
Import into a Database without transaction | Ousmane S, Ousmane E | Done | GUI | High | 24 | 3
Transaction mode | Ousmane S, Ousmane E | Working on it | GUI | Best effort | 72 | 3
Sprint review | Team | Done | GUI | Medium | 1 | 4
[5 empty] | 145 | 3.6/5